## Dashboard
Portfolio Healthcheck Dashboard
Automated assessment tool with scoring, RAG ratings, and recommended next steps
Portfolio Name:
Assessment Date: |  |  |  | Assessor:
Dimension | Score | Max | Percentage | RAG Rating | Link to Detail
Strategy |  | 24 |  |  | Go to Strategy Assessment
Governance |  | 24 |  |  | Go to Governance Assessment
Delivery |  | 24 |  |  | Go to Delivery Assessment
Resources |  | 24 |  |  | Go to Resources Assessment
Value |  | 24 |  |  | Go to Value Assessment
PMO Capability |  | 24 |  |  | Go to PMO Capability Assessment
TOTAL |  | 144
Overall Health Rating
Score Range | Rating | Interpretation
>83% | Green | Healthy — optimise and maintain
67-83% | Amber-Green | Generally healthy — address gaps
50-67% | Amber | Concerns — improvement plan needed
<50% | Red | Serious issues — transformation required
How to Use This Tool
1. Complete each dimension assessment tab by scoring each question from 1 (Red) to 4 (Green)
2. Scores automatically flow to this dashboard and calculate RAG ratings
3. Each dimension tab shows recommended next steps based on your average score
4. Use the suggested next steps to build an improvement action plan
5. Re-assess quarterly to track progress

## Strategy
Strategy Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Is the portfolio aligned to organisational strategy?
Are prioritisation criteria clear and consistently applied?
Is the portfolio appropriately balanced (Run/Grow/Transform)?
Is there a clear and healthy investment pipeline?
Are strategic objectives being achieved through portfolio delivery?
Is there a strong connection to business planning cycles?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
Strategy Red Flags
⚠ No clear strategic alignment between portfolio and organisational strategy
⚠ Too many priorities — inability to say no to new demand
⚠ Imbalanced portfolio (e.g. excessive Run, insufficient Transform)
⚠ Strategic drift going unchecked across the portfolio
⚠ Portfolio disconnected from business planning cycles
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Conduct an urgent strategic alignment review with executive team
• | Map every active investment to a strategic objective — stop anything that doesn't align
• | Establish a prioritisation framework with weighted criteria and enforce it immediately
• | Pause new intake until the current portfolio is rationalised
• | Create a portfolio balance target (Run/Grow/Transform) and begin rebalancing
• | Schedule a strategy-to-portfolio workshop with the executive sponsor
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Review and refresh the mapping between investments and strategic objectives
• | Strengthen the prioritisation process — ensure criteria are published and applied consistently
• | Assess portfolio balance and create a plan to close gaps in strategic coverage
• | Improve the investment pipeline by formalising the demand intake process
• | Establish a quarterly strategic alignment review with the Portfolio Board
• | Ensure business planning cycles feed into portfolio planning
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Fine-tune prioritisation criteria based on lessons learned
• | Review portfolio balance annually and adjust targets as strategy evolves
• | Strengthen the connection between strategic KPIs and portfolio performance metrics
• | Introduce horizon scanning to anticipate future strategic shifts
• | Share strategic alignment data more widely to build organisational understanding
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain current strong alignment practices
• | Consider advanced portfolio optimisation techniques (e.g. scenario modelling)
• | Benchmark against industry best practice for portfolio strategy alignment
• | Mentor other areas of the organisation on strategic portfolio management
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard

## Governance
Governance Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Is the portfolio governance structure effective?
Are investment decisions timely and evidence-based?
Is there appropriate executive engagement and sponsorship?
Are stage gates consistently applied across all investments?
Is portfolio reporting informing decisions (not just providing data)?
Are escalations handled appropriately and in a timely manner?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
Governance Red Flags
⚠ Decisions delayed, deferred, or circumvented
⚠ Executive disengagement from portfolio governance
⚠ Inconsistent application of stage gates
⚠ Reports not actionable — data without insight
⚠ Political decision-making overriding evidence
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Establish a Portfolio Board with clear terms of reference and decision rights
• | Define and publish escalation thresholds and paths
• | Implement mandatory stage gates for all investments above the threshold
• | Recruit or assign an executive sponsor for the portfolio
• | Create a basic portfolio reporting pack and agree the reporting cadence
• | Document and communicate the governance framework to all programme and project managers
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Review and strengthen Portfolio Board effectiveness — are decisions being made?
• | Ensure stage gate criteria are consistently applied and not bypassed
• | Improve reporting to focus on insight and recommended actions, not just data
• | Establish regular executive engagement cadence (monthly sponsor updates)
• | Implement a decision log to track and follow up on Portfolio Board decisions
• | Review escalation effectiveness — are issues being resolved at the right level?
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Refine decision rights matrix to ensure clarity at all levels
• | Introduce independent assurance reviews for high-value investments
• | Enhance reporting with trend analysis and forward-looking indicators
• | Conduct an annual governance effectiveness review
• | Benchmark governance against P3M3 or MoP standards
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain current governance standards and share best practice
• | Consider peer review or external audit of governance effectiveness
• | Explore advanced governance models (e.g. adaptive governance for agile portfolios)
• | Document and share governance lessons across the organisation
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard

## Delivery
Delivery Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Is overall delivery performance acceptable across the portfolio?
Are dependencies managed effectively across the portfolio?
Are risks aggregated and visible at portfolio level?
Is change control effective across programmes and projects?
Are projects and programmes closing successfully?
Is delivery capability improving over time?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
Delivery Red Flags
⚠ Multiple investments simultaneously in trouble
⚠ Unmanaged cross-programme dependencies causing failures
⚠ Risks not escalated or aggregated at portfolio level
⚠ Excessive project/programme churn (starting, stopping, restarting)
⚠ Repeat delivery failures with the same root causes
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Conduct an immediate portfolio delivery review — identify all Red/troubled investments
• | Create recovery plans for all critical investments or make stop decisions
• | Establish a dependency register and assign owners for all cross-programme dependencies
• | Implement portfolio-level risk aggregation and reporting
• | Enforce change control — no scope changes without impact assessment and approval
• | Review recent failures and extract lessons to prevent recurrence
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Strengthen dependency management with regular cross-programme coordination
• | Improve portfolio risk aggregation — look for themes and concentrations
• | Review change control effectiveness — is it proportionate and working?
• | Establish closure criteria and ensure post-implementation reviews happen
• | Identify common delivery issues and address root causes systematically
• | Introduce delivery confidence assessments for all investments
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Enhance delivery forecasting with earned value or similar techniques
• | Introduce proactive dependency management (anticipate, not just track)
• | Strengthen the lessons learned process and ensure insights drive improvement
• | Review delivery capability and invest in training where gaps exist
• | Consider independent delivery assurance for major investments
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain strong delivery performance and share best practice
• | Explore predictive analytics for delivery risk identification
• | Benchmark delivery performance against industry standards
• | Develop a delivery excellence community of practice
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard

## Resources
Resources Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Is resource capacity sufficient to meet current demand?
Are skills gaps identified and being actively addressed?
Is resource allocation based on portfolio priorities?
Is utilisation at healthy levels (80-85%)?
Are resource conflicts resolved promptly and fairly?
Is workforce planning effective for future needs?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
Resources Red Flags
⚠ Chronic over-allocation of key resources
⚠ Critical skills gaps with no plan to address them
⚠ Political resource allocation overriding priority-based decisions
⚠ High attrition of project and programme management staff
⚠ No visibility of resource capacity across the portfolio
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Create a basic resource capacity view — who do we have and where are they allocated?
• | Identify the top 3 critical skills gaps and create immediate sourcing plans
• | Establish the principle that resources are allocated by portfolio priority, not politics
• | Implement a simple resource request and allocation process
• | Address over-allocation immediately — no one should be allocated above 100%
• | Set up a monthly resource review with programme and project managers
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Build a skills matrix and use it to inform allocation decisions
• | Implement utilisation targets (80-85%) and track against them
• | Establish a formal resource conflict resolution process
• | Create a workforce plan that looks at least 6 months ahead
• | Improve visibility with a portfolio resource dashboard
• | Develop a sourcing strategy for scarce skills (contractors, training, recruitment)
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Refine capacity planning with scenario modelling for pipeline demand
• | Introduce resource forecasting aligned to the portfolio pipeline
• | Develop career pathways to improve retention of key staff
• | Optimise the mix of permanent, contract, and managed service resources
• | Benchmark utilisation and capacity metrics against industry norms
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain strong resource management practices
• | Explore strategic workforce planning aligned to multi-year portfolio strategy
• | Consider resource pooling or shared services models for efficiency
• | Invest in capability development to build internal capacity for future needs
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard

## Value
Value Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Are benefits being tracked and realised as planned?
Is return on investment being measured and achieved?
Are benefits owners actively engaged in realisation?
Is value-based decision making happening at portfolio level?
Are post-implementation reviews conducted for completed investments?
Is benefits performance improving over time?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
Value Red Flags
⚠ No benefits tracking in place across the portfolio
⚠ ROI not measured or reported for investments
⚠ Benefits owners disengaged after project approval
⚠ No post-implementation reviews being conducted
⚠ Declining benefits performance with no corrective action
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Establish a benefits management framework with clear definitions and ownership
• | Assign a named benefits owner for every active investment
• | Create a portfolio benefits register with measurable targets and baselines
• | Mandate benefits tracking as a condition of investment approval
• | Introduce post-implementation reviews for all completed investments
• | Report benefits realisation to the Portfolio Board quarterly
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Improve benefits measurement — ensure all benefits have quantified targets and baselines
• | Strengthen benefits owner engagement through regular reviews and accountability
• | Introduce ROI tracking and report it alongside delivery performance
• | Ensure post-implementation reviews happen consistently and findings are acted upon
• | Link benefits performance to future investment decisions
• | Develop benefits realisation plans for all major investments
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Enhance benefits forecasting and track forecast accuracy over time
• | Integrate benefits data into portfolio prioritisation and rebalancing decisions
• | Conduct portfolio-level benefits analysis (total value delivered vs invested)
• | Introduce benefits dependency mapping to understand enabling relationships
• | Share benefits success stories to build organisational commitment to value tracking
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain strong value management practices
• | Explore advanced value measurement (e.g. social value, strategic value beyond financial ROI)
• | Benchmark benefits realisation rates against industry standards
• | Develop a value management centre of excellence
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard

## PMO_Capability
PMO Capability Assessment
Score each question: 1 = Ineffective (Red) ¦ 2 = Partially effective (Amber) ¦ 3 = Effective (Light Green) ¦ 4 = Fully effective (Green)
Question | Score (1-4) | Evidence / Notes
Are PMO processes fit for purpose and proportionate?
Are tools and systems adequate for portfolio management?
Is project and programme management capability sufficient?
Is methodology consistently applied across the portfolio?
Is knowledge management effective (lessons learned, best practice)?
Is the PMO perceived as adding value by stakeholders?
TOTAL SCORE |  | Out of 24
AVERAGE SCORE
PMO Capability Red Flags
⚠ Processes seen as bureaucratic or routinely ignored
⚠ Tools not adopted or not fit for purpose
⚠ Significant PM capability gaps affecting delivery
⚠ Methodology applied variably or not at all
⚠ PMO perceived as overhead rather than value-add
Recommended Next Steps
Based on your average score, the following actions are recommended:
Score 1.0 - 1.9 (Red): Urgent Action Required
• | Define the PMO's purpose, scope, and service catalogue
• | Implement essential PMO processes: reporting, governance, resource management
• | Select and deploy a basic PPM tool to replace spreadsheet-based tracking
• | Assess PM capability gaps and create an urgent training plan
• | Standardise core templates and methodology — keep it simple and proportionate
• | Conduct a stakeholder survey to understand PMO perception and prioritise improvements
Score 2.0 - 2.6 (Amber): Improvement Needed
• | Review and streamline PMO processes — remove bureaucracy, add value
• | Improve PPM tool adoption through training and demonstrating benefits
• | Develop a PM competency framework and career pathway
• | Strengthen knowledge management — ensure lessons learned drive improvement
• | Introduce project sizing to tailor governance proportionately
• | Communicate PMO value through regular metrics and success stories
Score 2.7 - 3.3 (Amber-Green): Fine-Tune
• | Enhance PMO services based on stakeholder feedback
• | Invest in advanced PPM tool capabilities (dashboards, analytics, resource management)
• | Develop a PM community of practice for knowledge sharing
• | Introduce PMO maturity assessment and create a roadmap to the next level
• | Benchmark PMO services against P3M3 or similar maturity models
Score 3.4 - 4.0 (Green): Maintain Excellence
• | Maintain high PMO capability and continue to evolve services
• | Explore innovative practices (AI-assisted reporting, predictive analytics)
• | Position the PMO as a strategic partner, not just a support function
• | Share best practice externally and contribute to the PM profession
Your Recommended Actions (based on your score)
These actions are automatically selected based on your average score above.
Recommended Action
← Back to Dashboard